## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Research LLM evaluation, hallucination detection, RAG, RAGAS, and TruLens. | MUST HAVE | None |  | 3- Completed
Sprint 1 | Sprint 1 | US-02 | Design system architecture, agent responsibilities, scoring dimensions, and data models. | MUST HAVE | US-01 |  | 3- Completed
Sprint 1 | Sprint 1 | US-03 | Develop the single-evaluation input interface with validation. | MUST HAVE | US-02 |  | 3- Completed
Sprint 1 | Sprint 1 | US-04 | Prepare the reference knowledge base using benchmark datasets, chunking, embeddings, and vector search. | MUST HAVE | US-02 |  | 3- Completed
Sprint 2 | Sprint 2 | US-05 | Develop the Relevance Judge Agent with scores and reasoning. | MUST HAVE | US-03, US-04 |  | 3- Completed
Sprint 2 | Sprint 2 | US-06 | Develop the Accuracy Judge Agent with supporting evidence. | MUST HAVE | US-04 |  | 3- Completed
Sprint 2 | Sprint 2 | US-07 | Develop the Hallucination Detection Agent to identify unsupported or contradictory claims. | MUST HAVE | US-04 |  | 3- Completed
Sprint 2 | Sprint 2 | US-08 | Validate agent consistency using benchmark question-answer pairs. | MUST HAVE | US-05, US-06, US-07 |  | 3- Completed
Sprint 3 | Sprint 3 | US-09 | Develop the Completeness Judge Agent to identify missing information. | MUST HAVE | US-04 |  | 3- Completed
Sprint 3 | Sprint 3 | US-10 | Develop the Verdict Agent using weighted scores and verdict thresholds. | MUST HAVE | US-05, US-06, US-07, US-09 |  | 3- Completed
Sprint 3 | Sprint 3 | US-11 | Display dimension scores, reasoning, evidence, hallucination flags, and final verdict. | MUST HAVE | US-10 |  | 3- Completed
Sprint 3 | Sprint 3 | US-12 | Develop CSV-based batch evaluation with aggregated results. | MUST HAVE | US-10 |  | 3- Completed
Sprint 4 | Sprint 4 | US-13 | Develop the evaluation dashboard with statistics, charts, and verdict distribution. | MUST HAVE | US-12 |  | 3- Completed
Sprint 4 | Sprint 4 | US-14 | Implement dashboard filters for verdict, score range, and batch. | MUST HAVE | US-13 |  | 3- Completed
Sprint 4 | Sprint 4 | US-15 | Generate PDF reports for single evaluations. | MUST HAVE | US-11 |  | 3- Completed
Sprint 4 | Sprint 4 | US-16 | Generate PDF reports for batch evaluations. | MUST HAVE | US-12 |  | 3- Completed
Sprint 4 | Sprint 4 | US-17 | Test single evaluation, batch evaluation, filters, and PDF exports end to end. | MUST HAVE | US-14, US-15, US-16 |  | 3- Completed
Sprint 4 | Sprint 4 | US-18 | Evaluate responses from ChatGPT and Gemini and compare results. | MUST HAVE | US-10 |  | 3- Completed
Sprint 4 | Sprint 4 | US-19 | Prepare technical documentation, project report, and final demonstration. | MUST HAVE | US-17 |  | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG - Milestone 1: Foundation & Evaluation Understanding
US-01 | T-01 | Study LLM evaluation workflows, hallucination detection, factuality and faithfulness methods |  |  |  | Others | 3- Completed
US-01 | T-02 | Study RAG architecture, retrieval pipelines, embeddings, semantic similarity and vector search |  |  |  | Others | 3- Completed
US-01 | T-03 | Study LLM-as-a-Judge approaches; explore RAGAS and TruLens |  |  |  | Others | 3- Completed
US-01 | T-04 | Study TruthfulQA and SQuAD datasets; document findings, technology choices and strategy |  |  |  | Others | 3- Completed
US-02 | T-05 | Create system architecture diagram |  |  |  | Design | 3- Completed
US-02 | T-06 | Define responsibilities of Orchestrator and Relevance, Accuracy, Hallucination, Completeness and Verdict agents |  |  |  | Design | 3- Completed
US-02 | T-07 | Define scoring dimensions and scoring scale |  |  |  | Design | 3- Completed
US-02 | T-08 | Define orchestration flow, data models and end-to-end data flow |  |  |  | Design | 3- Completed
US-03 | T-09 | Build single evaluation submission interface |  |  |  | Coding | 3- Completed
US-03 | T-10 | Support question, AI response, optional reference answer and source document |  |  |  | Coding | 3- Completed
US-03 | T-11 | Implement input validation and error handling |  |  |  | Coding | 3- Completed
US-03 | T-12 | Store and process submitted inputs through backend/API layer |  |  |  | Coding | 3- Completed
US-04 | T-13 | Collect, clean and standardize TruthfulQA and SQuAD datasets |  |  |  | Build | 3- Completed
US-04 | T-14 | Define chunking strategy and generate embeddings |  |  |  | Build | 3- Completed
US-04 | T-15 | Implement vector store indexing with dataset, document, question, answer and chunk metadata |  |  |  | Build | 3- Completed
US-04 | T-16 | Build semantic retrieval and validate retrieval quality on benchmark questions |  |  |  | Unit Test | 3- Completed
SPRINT 2 BACKLOG - Milestone 2: Evaluation Judge Agents & Validation
US-05 | T-17 | Define relevance scoring scale and criteria |  |  |  | Design | 3- Completed
US-05 | T-18 | Implement Relevance Judge Agent with reasoning per evaluation |  |  |  | Coding | 3- Completed
US-05 | T-19 | Define structured I/O and integrate with Orchestrator and Input Module |  |  |  | Integration Test | 3- Completed
US-05 | T-20 | Test with relevant, partial, unrelated and off-topic benchmark pairs |  |  |  | Unit Test | 3- Completed
US-06 | T-21 | Define accuracy scoring scale and criteria |  |  |  | Design | 3- Completed
US-06 | T-22 | Implement comparison against reference answer, or RAG-retrieved chunks when unavailable |  |  |  | Coding | 3- Completed
US-06 | T-23 | Return score, reasoning and supporting evidence; integrate with Orchestrator |  |  |  | Integration Test | 3- Completed
US-06 | T-24 | Test with correct, incorrect and partially correct benchmark responses |  |  |  | Unit Test | 3- Completed
US-07 | T-25 | Implement claim extraction from AI response |  |  |  | Coding | 3- Completed
US-07 | T-26 | Cross-reference claims against RAG-retrieved chunks; flag unsupported/contradictory statements |  |  |  | Coding | 3- Completed
US-07 | T-27 | Return structured output (status, flagged claims, evidence, reasoning); integrate with Orchestrator |  |  |  | Integration Test | 3- Completed
US-07 | T-28 | Test with fully supported and partially unsupported responses |  |  |  | Unit Test | 3- Completed
US-08 | T-29 | Create evaluation test set from TruthfulQA, SQuAD and other benchmarks |  |  |  | Others | 3- Completed
US-08 | T-30 | Run test set through Relevance, Accuracy and Hallucination agents; compare expected vs actual |  |  |  | System Test | 3- Completed
US-08 | T-31 | Review reasoning quality; identify false positives/negatives and score inconsistencies |  |  |  | System Test | 3- Completed
US-08 | T-32 | Tune prompts, scoring criteria, retrieval settings and agent logic |  |  |  | Others | 3- Completed
SPRINT 3 BACKLOG - Milestone 3: Completeness, Verdict, Results Display & Batch Evaluation
US-09 | T-33 | Identify requirements and sub-questions in the submitted question |  |  |  | Coding | 3- Completed
US-09 | T-34 | Compare response against requirements (reference answer or RAG chunks); identify omissions |  |  |  | Coding | 3- Completed
US-09 | T-35 | Define completeness scale, structured output; integrate with Orchestrator |  |  |  | Integration Test | 3- Completed
US-09 | T-36 | Test with complete, partially complete and substantially incomplete responses |  |  |  | Unit Test | 3- Completed
US-10 | T-37 | Define weighted scoring model and score normalization |  |  |  | Design | 3- Completed
US-10 | T-38 | Define Pass / Needs Improvement / Fail thresholds and critical-failure rules |  |  |  | Design | 3- Completed
US-10 | T-39 | Implement overall score, verdict and consolidated reasoning summary; integrate with Orchestrator |  |  |  | Coding | 3- Completed
US-10 | T-40 | Validate verdicts across different score combinations |  |  |  | Unit Test | 3- Completed
US-11 | T-41 | Implement structured evaluation-result data models |  |  |  | Design | 3- Completed
US-11 | T-42 | Build results interface: dimension scores, reasoning and supporting evidence |  |  |  | Coding | 3- Completed
US-11 | T-43 | Display hallucinated claims, missing aspects, overall score, verdict and visual indicators |  |  |  | Coding | 3- Completed
US-11 | T-44 | Connect to Orchestrator/backend and test with varied result combinations |  |  |  | Integration Test | 3- Completed
US-12 | T-45 | Define CSV format; implement upload, validation and parsing |  |  |  | Coding | 3- Completed
US-12 | T-46 | Process valid records through Orchestrator; store individual results; handle failures without stopping batch |  |  |  | Coding | 3- Completed
US-12 | T-47 | Build results table, record drill-down and progress/status display |  |  |  | Coding | 3- Completed
US-12 | T-48 | Calculate batch statistics; test with small and large CSV files |  |  |  | System Test | 3- Completed
SPRINT 4 BACKLOG - Milestone 4: Dashboard, Report Export, End-to-End Testing & Final Demonstration
US-13 | T-49 | Display total responses, verdict counts/percentages and average dimension scores |  |  |  | Coding | 3- Completed
US-13 | T-50 | Build score distribution, hallucination and incompleteness charts |  |  |  | Coding | 3- Completed
US-13 | T-51 | Add batch trends, top evaluation issues and drill-down to individual results |  |  |  | Coding | 3- Completed
US-13 | T-52 | Validate dashboard statistics against stored evaluation records |  |  |  | Unit Test | 3- Completed
US-14 | T-53 | Implement verdict filter |  |  |  | Coding | 3- Completed
US-14 | T-54 | Implement score-range filter |  |  |  | Coding | 3- Completed
US-14 | T-55 | Implement batch filter and combined filtering |  |  |  | Coding | 3- Completed
US-14 | T-56 | Test filters against underlying records |  |  |  | Unit Test | 3- Completed
US-15 | T-57 | Define single-evaluation report structure |  |  |  | Design | 3- Completed
US-15 | T-58 | Generate PDF with scores, reasoning, evidence, hallucination flags and verdict |  |  |  | Coding | 3- Completed
US-15 | T-59 | Format long text without overlap or missing content |  |  |  | Coding | 3- Completed
US-15 | T-60 | Validate PDF content against evaluation record |  |  |  | Unit Test | 3- Completed
US-16 | T-61 | Define batch report structure with metadata and batch statistics |  |  |  | Design | 3- Completed
US-16 | T-62 | Add dimension breakdowns, flagged responses and improvement recommendations |  |  |  | Coding | 3- Completed
US-16 | T-63 | Add tables, charts and visual indicators; export option after batch evaluation |  |  |  | Coding | 3- Completed
US-16 | T-64 | Test PDF generation with small and large batches |  |  |  | Unit Test | 3- Completed
US-17 | T-65 | End-to-end test of single-evaluation workflow |  |  |  | System Test | 3- Completed
US-17 | T-66 | End-to-end test of batch workflow, dashboard and report export |  |  |  | System Test | 3- Completed
US-17 | T-67 | Test error handling, no-reference (RAG-only) evaluation and agent scoring consistency |  |  |  | System Test | 3- Completed
US-17 | T-68 | Dashboard and PDF correctness checks; performance test with larger batches |  |  |  | System Test | 3- Completed
US-18 | T-69 | Prepare question-answer datasets for ChatGPT and Gemini |  |  |  | Others | 3- Completed
US-18 | T-70 | Run both AI systems through the validation platform and capture results |  |  |  | System Test | 3- Completed
US-18 | T-71 | Compare evaluation outputs across the two systems by dimension |  |  |  | Others | 3- Completed
US-19 | T-72 | Prepare technical documentation (architecture, agents, scoring model, RAG, APIs, CSV, dashboard, PDF) |  |  |  | Others | 3- Completed
US-19 | T-73 | Prepare final project report |  |  |  | Others | 3- Completed
US-19 | T-74 | Prepare and conduct final end-to-end demonstration |  |  |  | Others | 3- Completed

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Sprint Summary
Sprint | Milestone | Sprint Title | Scope | User Stories | Outcome
Sprint 1 | M1 | Foundation and Evaluation Understanding | Research evaluation methods, design the architecture, define the evaluation workflow, and establish the input and reference knowledge-base modules. | US-01 to US-04 | Completed. Research documented, architecture and data models designed, single-evaluation input module built, and benchmark-based reference knowledge base (TruthfulQA, SQuAD) indexed with semantic retrieval.
Sprint 2 | M2 | Evaluation Judge Agents | Develop relevance, accuracy, and hallucination detection agents. Validate their scores, reasoning, and consistency against representative question-answer examples. | US-05 to US-08 | Completed. Relevance, Accuracy and Hallucination Detection agents built and integrated with the Orchestrator; consistency validated on benchmark question-answer pairs.
Sprint 3 | M3 | Completeness, Verdict, and Batch Evaluation | Implement completeness scoring, weighted verdict generation, detailed results display, and CSV batch evaluation. | US-09 to US-12 | Completed. Completeness agent, weighted Verdict agent, per-dimension results display and CSV batch evaluation with aggregated results delivered and tested.
Sprint 4 | M4 | Dashboard, Reports, and Testing | Develop the dashboard and its filters, generate single and batch PDF reports, test end-to-end workflows, and compare ChatGPT and Gemini responses. | US-13 to US-19 | Completed. Dashboard with filters, single and batch PDF reports, end-to-end testing, ChatGPT vs Gemini comparison, documentation, project report and final demonstration.
Sprint 4 - Recorded Dashboard Snapshot
Total responses |  | 155
Average final score |  | 0.72
PASS |  | 92
NEEDS IMPROVEMENT |  | 12
FAIL |  | 51
Hallucination cases |  | 16
Check: PASS + NEEDS IMPROVEMENT + FAIL |  | 155 | Matches total responses
Source: dashboard snapshot supplied by the project owner (blue = input values).

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7